## PLAN
2026 - 2028 Strategic Plan Mission: To promote a high standard of professionalism by empowering our members through education, advocacy and outreach. Vision: To positively impact the real estate industry and our community.
PILLAR #1 | EDUCATION | Primary Owners | Due Date | Date Completed | Notes
PILLAR OBJECTIVE | To provide members with knowledge, tools, and training
| Action Step: To promote available opportunities for members to complete required education | R-BAR Staff | Ongoing |  | Place extra focus on CE and COE/Fair Housing years.
| Action Step: To conduct a minimum of 12 educational opportunities per year including 1 Fair Housing event, CIC Events, and other R-BAR opportunities | Education and DEI Committees, CIC | Q4 of Each Year
| Action Step: To conduct a yearly evaluation of New Member Orientation utilizing member feedback surveys and make adjustments based on feedback. | R-BAR Staff and Education Committee | Q4 of Each Year
| Action Step: To create 3 new resources for members a year on educational topics | R-BAR Staff and Education Committee | Q4 of Each Year
PILLAR #2 | ADVOCACY | Owners | Due Date | Date Completed | Notes
PILLAR OBJECTIVE | To promote homeownership and private property rights
| Action Step: Increase R-PAC Participation by 10% each year. | R-BAR Government Affairs Committee, RPAC Trustees, Board of Directors | Q4 of Each Year |  | 2025 Benchmark:
| Action Step: Complete an average of 10 interactions per month with municipal officials. | Government Affairs Director and R-BAR Staff, Government Affairs Committee, RPAC Trustees | Q4 of Each Year
| Action Step: Complete an average of 10 interactions per month with other industry partners (GRCA, other community organizations, etc.) | Government Affairs Director and R-BAR Staff, CIC | Q4 of Each Year
| Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners | R-BAR Staff, Government Affairs Committee, RPAC Trustees, CIC, DEI | Q4 of Each Year
PILLAR #3 | OUTREACH | Owners | Due Date | Date Completed | Notes
PILLAR OBJECTIVE | To engage members and build community connections.
| Action Step: Offer one opportunity per year to specifically engage new R-BAR members (from 0 - 18 months of membership) | R-BAR Staff, Board of Directors | Q4 of Each Year
| Action Step: Increase member engagement by requiring Board Members to bring 2 R-BAR members per year to an R-BAR event. | Board of Directors | Q4 of Each Year
| Action Step: Engage with one new community partner per year. | Board of Directors, R-BAR Staff, CIC, all other Committees | Q4 of Each Year
| Action Step: Conduct a minimum of 6 community outreach events/activities per year. | Outreach and DEI Committees | Q4 of Each Year
| Action Step: Apply for and utilize at least 1 NAR Grant per year for outreach purposes (if grants are available) | R-BAR Staff, Outreach and DEI Committees, CIC | Q4 of Each Year
PILLAR #4 | OPERATIONS | Owners | Due Date | Date Completed | Notes
PILLAR OBJECTIVE | To ensure organizational long-term stability.
| Action Step: Redesign the Association webite. | R-BAR Staff, Board of Directors | Q4 2028
| Action Step: Conduct a minimum of 1 fundraising event per year to benefit R-BAR | Board of Directors, Finance Committee, R-BAR Staff | Q4 of Each Year
| Action Step: Gain 10 new affiliates per year with a net increase of 5 | Board of Directors, Committees, CIC, RBAR Staff | Q4 of Each Year
| Action Step: Implement a minimum of 2 non-dues revenue opportunities per year (outside of fundraising events) | R-BAR Staff, Committees | Q4 of Each Year
| Action Step: Conduct a yearly review of benefits and sponsorship program for potential expansion | R-BAR Staff, Affiliate Advisory Committee | Q2 of Each Year |  | Review In Q2 for advertising in Q3 Dues season
| Action Step: Document, implement, and promote pathways to leadership opportunities within R-BAR | Board of Directors, Committes, CIC, R-BAR Staff | Ongoing

## LIST FOR COMMITTEES
Row Labels
Affiliate Advisory Committee
PILLAR #4: OPERATIONS
Action Step: Conduct a yearly review of benefits and sponsorship program for potential expansion
All Committees
PILLAR #3: OUTREACH
Action Step: Engage with one new community partner per year.
PILLAR #4: OPERATIONS
Action Step: Gain 10 new affiliates per year with a net increase of 5
Action Step: Document, implement, and promote pathways to leadership opportunities within R-BAR
Action Step: Implement a minimum of 2 non-dues revenue opportunities per year (outside of fundraising events)
Board of Directors
PILLAR #2: ADVOCACY
Action Step: Increase R-PAC Participation by 10% each year.
PILLAR #3: OUTREACH
Action Step: Engage with one new community partner per year.
Action Step: Increase member engagement by requiring Board Members to bring 2 R-BAR members per year to an R-BAR event.
Action Step: Offer one opportunity per year to specifically engage new R-BAR members (from 0 - 18 months of membership)
PILLAR #4: OPERATIONS
Action Step: Gain 10 new affiliates per year with a net increase of 5
Action Step: Redesign the Association webite.
Action Step: Conduct a minimum of 1 fundraising event per year to benefit R-BAR
Action Step: Document, implement, and promote pathways to leadership opportunities within R-BAR
CIC
PILLAR #1: EDUCATION
Action Step: To conduct a minimum of 12 educational opportunities per year including 1 Fair Housing event, CIC Events, and other R-BAR opportunities
PILLAR #2: ADVOCACY
Action Step: Complete an average of 10 interactions per month with other industry partners (GRCA, other community organizations, etc.)
Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners
PILLAR #3: OUTREACH
Action Step: Apply for and utilize at least 1 NAR Grant per year for outreach purposes (if grants are available)
Action Step: Engage with one new community partner per year.
PILLAR #4: OPERATIONS
Action Step: Gain 10 new affiliates per year with a net increase of 5
Action Step: Document, implement, and promote pathways to leadership opportunities within R-BAR
DEI Committee
PILLAR #1: EDUCATION
Action Step: To conduct a minimum of 12 educational opportunities per year including 1 Fair Housing event, CIC Events, and other R-BAR opportunities
PILLAR #2: ADVOCACY
Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners
PILLAR #3: OUTREACH
Action Step: Apply for and utilize at least 1 NAR Grant per year for outreach purposes (if grants are available)
Action Step: Conduct a minimum of 6 community outreach events/activities per year.
Education Committee
PILLAR #1: EDUCATION
Action Step: To conduct a yearly evaluation of New Member Orientation utilizing member feedback surveys and make adjustments based on feedback.
Action Step: To create 3 new resources for members a year on educational topics
Action Step: To conduct a minimum of 12 educational opportunities per year including 1 Fair Housing event, CIC Events, and other R-BAR opportunities
Finance Committee
PILLAR #4: OPERATIONS
Action Step: Conduct a minimum of 1 fundraising event per year to benefit R-BAR
Government Affairs Committee
PILLAR #2: ADVOCACY
Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners
Action Step: Complete an average of 10 interactions per month with municipal officials.
Action Step: Increase R-PAC Participation by 10% each year.
Government Affairs Director
PILLAR #2: ADVOCACY
Action Step: Complete an average of 10 interactions per month with other industry partners (GRCA, other community organizations, etc.)
Action Step: Complete an average of 10 interactions per month with municipal officials.
Outreach Committee
PILLAR #3: OUTREACH
Action Step: Apply for and utilize at least 1 NAR Grant per year for outreach purposes (if grants are available)
Action Step: Conduct a minimum of 6 community outreach events/activities per year.
R-BAR Staff
PILLAR #1: EDUCATION
Action Step: To conduct a yearly evaluation of New Member Orientation utilizing member feedback surveys and make adjustments based on feedback.
Action Step: To create 3 new resources for members a year on educational topics
Action Step: To promote available opportunities for members to complete required education
PILLAR #2: ADVOCACY
Action Step: Complete an average of 10 interactions per month with other industry partners (GRCA, other community organizations, etc.)
Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners
Action Step: Complete an average of 10 interactions per month with municipal officials.
PILLAR #3: OUTREACH
Action Step: Apply for and utilize at least 1 NAR Grant per year for outreach purposes (if grants are available)
Action Step: Engage with one new community partner per year.
Action Step: Offer one opportunity per year to specifically engage new R-BAR members (from 0 - 18 months of membership)
PILLAR #4: OPERATIONS
Action Step: Gain 10 new affiliates per year with a net increase of 5
Action Step: Redesign the Association webite.
Action Step: Conduct a minimum of 1 fundraising event per year to benefit R-BAR
Action Step: Conduct a yearly review of benefits and sponsorship program for potential expansion
Action Step: Document, implement, and promote pathways to leadership opportunities within R-BAR
Action Step: Implement a minimum of 2 non-dues revenue opportunities per year (outside of fundraising events)
RPAC Trustees
PILLAR #2: ADVOCACY
Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners
Action Step: Complete an average of 10 interactions per month with municipal officials.
Action Step: Increase R-PAC Participation by 10% each year.
Grand Total

## WORKING GROUPS
2026 - 2028 Strategic Plan: ACTION STEPS BY WORKING GROUP Mission: To promote a high standard of professionalism by empowering our members through education, advocacy and outreach. Vision: To positively impact the real estate industry and our community.
PILLAR | ACTION | OWNER
PILLAR #1: EDUCATION | Action Step: To conduct a minimum of 12 educational opportunities per year including 1 Fair Housing event, CIC Events, and other R-BAR opportunities | CIC
PILLAR #1: EDUCATION | Action Step: To conduct a minimum of 12 educational opportunities per year including 1 Fair Housing event, CIC Events, and other R-BAR opportunities | DEI Committee
PILLAR #1: EDUCATION | Action Step: To conduct a minimum of 12 educational opportunities per year including 1 Fair Housing event, CIC Events, and other R-BAR opportunities | Education Committee
PILLAR #1: EDUCATION | Action Step: To conduct a yearly evaluation of New Member Orientation utilizing member feedback surveys and make adjustments based on feedback. | Education Committee
PILLAR #1: EDUCATION | Action Step: To create 3 new resources for members a year on educational topics | Education Committee
PILLAR #1: EDUCATION | Action Step: To promote available opportunities for members to complete required education | R-BAR Staff
PILLAR #1: EDUCATION | Action Step: To conduct a yearly evaluation of New Member Orientation utilizing member feedback surveys and make adjustments based on feedback. | R-BAR Staff
PILLAR #1: EDUCATION | Action Step: To create 3 new resources for members a year on educational topics | R-BAR Staff
PILLAR #2: ADVOCACY | Action Step: Increase R-PAC Participation by 10% each year. | Board of Directors
PILLAR #2: ADVOCACY | Action Step: Complete an average of 10 interactions per month with other industry partners (GRCA, other community organizations, etc.) | CIC
PILLAR #2: ADVOCACY | Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners | CIC
PILLAR #2: ADVOCACY | Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners | DEI Committee
PILLAR #2: ADVOCACY | Action Step: Complete an average of 10 interactions per month with municipal officials. | Government Affairs Committee
PILLAR #2: ADVOCACY | Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners | Government Affairs Committee
PILLAR #2: ADVOCACY | Action Step: Complete an average of 10 interactions per month with municipal officials. | Government Affairs Director
PILLAR #2: ADVOCACY | Action Step: Complete an average of 10 interactions per month with other industry partners (GRCA, other community organizations, etc.) | Government Affairs Director
PILLAR #2: ADVOCACY | Action Step: Increase R-PAC Participation by 10% each year. | Government Affairs Committee
PILLAR #2: ADVOCACY | Action Step: Complete an average of 10 interactions per month with municipal officials. | R-BAR Staff
PILLAR #2: ADVOCACY | Action Step: Complete an average of 10 interactions per month with other industry partners (GRCA, other community organizations, etc.) | R-BAR Staff
PILLAR #2: ADVOCACY | Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners | R-BAR Staff
PILLAR #2: ADVOCACY | Action Step: Increase R-PAC Participation by 10% each year. | RPAC Trustees
PILLAR #2: ADVOCACY | Action Step: Promote a minumum of 1 Fair Housing initiative per year to municipal officials and other community partners | RPAC Trustees
PILLAR #2: ADVOCACY | Action Step: Complete an average of 10 interactions per month with municipal officials. | RPAC Trustees
PILLAR #3: OUTREACH | Action Step: Engage with one new community partner per year. | All Committees
PILLAR #3: OUTREACH | Action Step: Engage with one new community partner per year. | Board of Directors
PILLAR #3: OUTREACH | Action Step: Offer one opportunity per year to specifically engage new R-BAR members (from 0 - 18 months of membership) | Board of Directors
PILLAR #3: OUTREACH | Action Step: Increase member engagement by requiring Board Members to bring 2 R-BAR members per year to an R-BAR event. | Board of Directors
PILLAR #3: OUTREACH | Action Step: Engage with one new community partner per year. | CIC
PILLAR #3: OUTREACH | Action Step: Apply for and utilize at least 1 NAR Grant per year for outreach purposes (if grants are available) | CIC
PILLAR #3: OUTREACH | Action Step: Conduct a minimum of 6 community outreach events/activities per year. | DEI Committee
PILLAR #3: OUTREACH | Action Step: Apply for and utilize at least 1 NAR Grant per year for outreach purposes (if grants are available) | DEI Committee
PILLAR #3: OUTREACH | Action Step: Conduct a minimum of 6 community outreach events/activities per year. | Outreach Committee
PILLAR #3: OUTREACH | Action Step: Apply for and utilize at least 1 NAR Grant per year for outreach purposes (if grants are available) | Outreach Committee
PILLAR #3: OUTREACH | Action Step: Offer one opportunity per year to specifically engage new R-BAR members (from 0 - 18 months of membership) | R-BAR Staff
PILLAR #3: OUTREACH | Action Step: Engage with one new community partner per year. | R-BAR Staff
PILLAR #3: OUTREACH | Action Step: Apply for and utilize at least 1 NAR Grant per year for outreach purposes (if grants are available) | R-BAR Staff
PILLAR #4: OPERATIONS | Action Step: Conduct a yearly review of benefits and sponsorship program for potential expansion | Affiliate Advisory Committee
PILLAR #4: OPERATIONS | Action Step: Gain 10 new affiliates per year with a net increase of 5 | All Committees
PILLAR #4: OPERATIONS | Action Step: Implement a minimum of 2 non-dues revenue opportunities per year (outside of fundraising events) | All Committees
PILLAR #4: OPERATIONS | Action Step: Document, implement, and promote pathways to leadership opportunities within R-BAR | All Committees
PILLAR #4: OPERATIONS | Action Step: Conduct a minimum of 1 fundraising event per year to benefit R-BAR | Board of Directors
PILLAR #4: OPERATIONS | Action Step: Gain 10 new affiliates per year with a net increase of 5 | Board of Directors
PILLAR #4: OPERATIONS | Action Step: Document, implement, and promote pathways to leadership opportunities within R-BAR | Board of Directors
PILLAR #4: OPERATIONS | Action Step: Redesign the Association webite. | Board of Directors
PILLAR #4: OPERATIONS | Action Step: Gain 10 new affiliates per year with a net increase of 5 | CIC
PILLAR #4: OPERATIONS | Action Step: Document, implement, and promote pathways to leadership opportunities within R-BAR | CIC
PILLAR #4: OPERATIONS | Action Step: Conduct a minimum of 1 fundraising event per year to benefit R-BAR | Finance Committee
PILLAR #4: OPERATIONS | Action Step: Redesign the Association webite. | R-BAR Staff
PILLAR #4: OPERATIONS | Action Step: Conduct a minimum of 1 fundraising event per year to benefit R-BAR | R-BAR Staff
PILLAR #4: OPERATIONS | Action Step: Gain 10 new affiliates per year with a net increase of 5 | R-BAR Staff
PILLAR #4: OPERATIONS | Action Step: Implement a minimum of 2 non-dues revenue opportunities per year (outside of fundraising events) | R-BAR Staff
PILLAR #4: OPERATIONS | Action Step: Conduct a yearly review of benefits and sponsorship program for potential expansion | R-BAR Staff
PILLAR #4: OPERATIONS | Action Step: Document, implement, and promote pathways to leadership opportunities within R-BAR | R-BAR Staff